Field Day Preparation

Pleasant Ridge Elementary

Student Head Count 2014- 450

April to Dos:

- Meet with Mr. Welton/PE to determine date of Field Day, scope of field day activities, and help needed. Local and other participants helped in 2014- see details below.  Make list of activities needing outside help/volunteering.

- Determine Budget- ask PTA representative.

- Determine T-shirt process for current year- in the past Mr. Welton has taken care of all of this.

- Solicit Donations of Water (2014-Buschs donated  10 cases of water=240). PTA covered additional 12 cases, and 1000 freeze pops (2 per student). If soliciting of donations is earlier then the additional water and freeze pops may also be donated leaving funds for other activities. Buschs also delivered the water to the school. Other stores may have cheaper water- but since Buschs were willing to deliver it the morning of Field Day- it was very helpful.

May to Dos:

- Circulate volunteer form (see form) to students in school by classroom. Also email the form to Mr. Bezeau so it can be included in weekly email updates for May leading up to Field Day. Have the forms returned to the classroom teacher at least 2 weeks prior to event, then have classroom teacher deliver to Mr. Welton.  In 2014, Field Day chair collected these forms and made a list of morning and afternoon volunteers, and contacted those volunteers with Field Day information 1 week prior to event.

- 2 weeks prior to event- have Freeze pops in house and place in freezer- so they will be frozen on the event day. In 2014 we were given space in PR cafeteria freezer. Mr. Tracy helped with that.

- Week of event- confirm water donations and delivery. Have water delivered to PR on Field Day Date at 8 am by front doors. It can just be left outside.

- Week of event- confirm outside volunteer participation.  Check on freeze pops-determine how these will be distributed. Last year we delivered them to classrooms at a later date. But it may be beneficial to let teachers know in advance these will be distributed at end of day on Field Day.

- Day before event- Help Mr. Welton get materials organized for set up. He has a planned map for activities. Your job is to help him execute and help with tear down.

- Set up water station outside main doors. Goal is one bottle per student.

- Day of Field Day: Confirm water again. Help set up if needed.

Field Day-Event Details

- Check in with Mr. Welton for any last minute details. He will have activities set up around school.

- Make certain volunteer check in table is set up with sign in and volunteer stickers. Most of the volunteer needs are staying at a station and keeping the kids safe-so encourage volunteers to do this first.

- Check stations.

- Monitor stations and school grounds as children rotate through. Especially bounce houses for controlled flow.

- Once event is completed assist with tear down and clean up.

Following Outside Participants from 2014 (Mr. Welton will also have a list that may enhance).

Contact in April to generate participation.

1. Workout 1 Saline- Donated equipment for a station, but we had a volunteer execute it.

2. Gym America

3. SASA

4. Saline High Sports teams- mens baseball and womens softball- Mr. Welton coordinated this.

5. SkyZone- Aldra- contact- Phone: 810-923-9223- they had a game set up and gave away passes for jump time.

6. Saline Rec Center- Bounce houses

Ideas for other participants for Future:

1. Fire Department- spray fire hose , look at Fire Truck

2. Police Department- Police Car/truck- kids get to peek inside, siren demos etc

3. Contact PTA - determine use of some of budget for inflatable zip line rental, or bigger bounce house rental.

4. Contact MI Football or other sports teams to come set up games

5. Martial Arts Academy

6. Some sort of small maze to navigate through.

My contact information:

2014 PR Field Day

kristahopson@gmail.com

734-255-0794

Joseph Welton- Pleasant Ridge PE Teacher

weltonj@salineschools.org